## Sheet1
ChileWic Product Backlog
Entrega | Tarea | Sprint Ready | Prioridad | Estatus | Puntos de Historia | Asignado a un Sprint
2019-05-16 | Sprint 1 | Yes | High | In Progress | 24
| Crear Bootstrap | Yes | High | In Progress | 4 | Yes
| Crear Login | Yes | Medium | In Progress | 8 | Yes
| Crear Roles | Yes | High | In Progress | 5 | Yes
| Crear Registro de Asistencia | Yes | High | In Progress | 4 | Yes
| Eliminar Registro de Asistencia | Yes | Medium | In Progress | 1 | Yes
| Ver Asistentes registrados | Yes | Medium | In Progress | 2 | Yes
2019-06-13 | Sprint 2 | No | High | Not Started | 42 | Yes
| Registrar Propuesta a charlas | No | High | Not Started | 5 | Yes
| Modificar Propuesta a charlas | No | High | Not Started | 3 | Yes
| Ver Propuesta a charlas | No | High | Not Started | 2 | Yes
| Eliminar Propuesta a charlas | No | High | Not Started | 2 | Yes
| Asignar Revisadores | No | High | Not Started | 10 | Yes
| Seleccionar propuestas(Revisadores) | No | High | Not Started | 5 | Yes
| Sistema autmático de asignacion de Revision | No | High | Not Started | 15 | No
2019-06-23 | Sprint 3 | No | Medium | Not Started | 32 | No
| Sistema de Presupuestos | No | Low | Not Started | 8 | No
| Creador de Programa | No | High | Not Started | 8 | No
| Task 9 | No | Medium | Not Started | 16 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started