## Sheet1
Task Name | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint 1 | No | High | In Progress | 46 | No
Crear Bootstrap | Yes | High | In Progress | 8 | Yes
Crear Login | Yes | Medium | In Progress | 16 | Yes
Crear Roles | Yes | High | In Progress | 10 | Yes
Crear Registro de Asistencia | Yes | High | In Progress | 8 | Yes
Ver Asistentes registrados | Yes | Medium | In Progress | 4 | Yes
Sprint 2 | Yes | Medium | In Progress | 96 | Yes
Task 4 | Yes | Low | Complete | 32 | Yes
Task 5 | Yes | Low | Complete | 48 | Yes
Task 6 | No | Medium | Not Started | 16 | No
Sprint 3 | No | Medium | In Progress | 32 | No
Task 7 | No | Low | In Progress | 8 | No
Task 8 | Yes | Medium | In Progress | 8 | No
Task 9 | No | Medium | In Progress | 16 | No

## Sheet2
This sheet is to enable the drop-down lists
Yes | High | Complete
No | Medium | In Progress
| Low | Not Started